## Sheet1
SOW
|  | Joe | Bob | Steve | Jerry
| build |  |  |  |  | Objective | time to perform
2002-01-07 | B8c | DT-1 #1 | S-1 #1 | overhead | overhead | DT-1 | 1d | Component-A
2002-01-08 |  | RT-1 #1 |  | overhead | overhead | DT-1 oper | 1d | Component-A live
2002-01-09 |  |  |  | open | DT-1 oper #1 | DT-3 | free | SDK
2002-01-10 | handoff | reburn day | reburn day | open |  | DT-4 | 1d | Test application
2002-01-11 |  | slack | slack | slack | slack | DT-5 | .5d | Transation tests
2002-01-12 |  | slack | slack | slack | slack | DT-6 | .5d | Sample application tests
2002-01-13 | handoff | overhead | overhead | overhead | overhead | RT-1 | 2+1d | Primary validation
2002-01-14 | B8d | DT-1 #2 | DT-6 #1 | RT-10 dmz #1 | RT-3 #1 | RT-2 | 2d | System testing
2002-01-15 | cycle 1 | RT-1 #2 | S-1 #2 |  | DT-5 #1 | RT-3 | 1d | Stress suite
2002-01-16 |  |  |  | RT-2 #1 | RT-4 #1 | RT-4 | 2d > 1d | Management verification
2002-01-17 | handoff | reburn day | reburn day |  |  | RT-7 | 1d | Deployment
2002-01-18 |  | slack | reburn day |  | slack | RT-9 | 1d | Regression
2002-01-19 |  | slack | slack | slack | slack | RT-10 dmz | 2d | DMZ testing
2002-01-20 |  | overhead | overhead | overhead | overhead | RT-11 dmz | free | Connecters testing
2002-01-21 | B8e | DT-1 #3 | RT-2 #2 | S-4 dmz #1 | RT-1 #3 | S-1 | 3d > 2d | Primary validation for Solaris
2002-01-22 | cycle 2 | S-3 #1 | S-1 #3 |  |  | S-2 | 2d | Func Regression
2002-01-23 | move | overhead |  | overhead | reburn day | S-3 | 2d | Regression
2002-01-24 | move/handoff | overhead | reburn day | overhead | DT-4 #1 | S-4 dmz | 4d > 3d | DMZ testing
2002-01-25 |  | slack | reburn day | slack | slack
2002-01-26 |  | slack | slack | slack | slack
2002-01-27 |  |  | RT-4 #2 |  | overhead |  | =Verification Testing
2002-01-28 | B8f | DT-1 #4 | RT-7 #1 |  | RT-3 #2 |  | = specifically SQA testing
2002-01-29 | cycle 3 | RT-1 #4 | S-1 #4 | RT-10 dmz #2 | DT-4 #2 |  | = specifically component or dev testing
2002-01-30 |  |  |  |  | RS-3 #1 | overhead | = overhead days, includes time with devs to solve problems and do investigations
2002-01-31 | handoff | reburn day | reburn day | RT-11 |  | reburn day | = planned re-do
2002-02-01 |  | slack | reburn day | slack | slack | open | = free
2002-02-02 |  | slack | slack | slack | slack
2002-02-03 |  | overhead | overhead | overhead | overhead
2002-02-04 | RC1 | DT-1 #5 | S-1 #5 | RT-10 dmz #3 | RT-2 #2
2002-02-05 |  | RT-1 #5
2002-02-06 |  |  | reburn day |  | DT-6 #1
2002-02-07 | handoff | reburn day | open | DT-4 #3 | DT-5 #1
2002-02-08 |  | slack | slack | slack | slack
2002-02-09 |  | slack | slack | slack | slack
2002-02-10 |  | overhead | overhead | overhead | overhead
2002-02-11 | RC2 | DT-1 #6 | DT-1 oper #6 | S-1 #5 | RT-3 #3
2002-02-12 |  | RT-1 #6 | RT-9 #1 |  | RT-4 #2
2002-02-13 |  |  | open | S-3 #2 | open
2002-02-14 |  | open | open |  | open