## Sheet1
Tasking for week 18 December
| machine | owner | task | Done
Primary
| Indium | Bob | Load first JProduct-A webserver
| Argon | Bob | Load first JProduct-A dispatcher
| Lead | Bob | update level-1 Application-F UI
| Uranium | Bob | update level-1 Application-F business services (jars only)
| Unranium | Bob | compelte level-1 routing and release to QA
Secondary
gmp
| all | vu | ghost
| Chlorine | hanson | load Application-F 3.0 services
| Chlorine | Joe | integrate Mailbox services
| Helium | john | load Portal 4.0
| Helium | hanson | integrate Application-F 3.0 UI
| Helium | engineers | integrate Application-G 1.0
| Calcium | john | load CE 2.1
| Neon | john | load Siteminder
| Neon | john | load roundtrip
| Neon/Hydrogen | Joe/erich | set rounting relationships
| Neon/Hydrogen | Joe/erich | investigate which partners are working through single-sign on to Application-F
nmm
| Gallium | engineers | load Webserver w/ Portal 4.0
| Gallium | engineers | integrate Webserver w/ Application-F 2.2
| Lithium | engineers | load Application-FCK 1.0 w/ Application-F 2.2 services
| Potassium | engineers | load Central DB
| Beryllium | engineers | load Product-O 2.1
| Strontium | engineers | load Product-A 6.5
sfr | Xenon | Joe | refresh L2 Application-F
| Xenon | Joe | update routes for NMM
| Xenon | engineers | load Bonus Pack for NMM
| Radium | Joe | load SDK 4.0
| Radium | Joe | load Application-F 3.0 services
| Radium | Joe | route hosted suppliers from Boron to Radium
| Indium | Bob | Webserver
| Argon | Bob | Dispatcher and DB
ebd
| Plutonium | Joe | move Product-A 7.0 Webserver from level-1 to edb
| Titanium | Joe | move Product-A 7.0 dispatcher and DB from level-1 to ebd
Testing
| All | Bob | Planned solution testing
| SFR | Bob | Verify single-sign on with Application-F3.0 on Portal 3.2
| SFR | mix | Verify transactions in sfr