## Pred. Bug Model
Cycle
| Pre-functional Test |  |  |  |  | Functional Test |  |  | System Test |  |  | Acceptance
| QI | QII | QIII | QIV | QV | QVI | QVII | QVIII | QIX | QX | QXI | QXII | QXIII
| 1997-09-29 | 1997-10-31 | 1997-12-02 | 1997-12-15 | 1997-12-29 | 1998-01-12 | 1998-01-26 | 1998-02-09 | 1998-02-23 | 1998-03-16 | 1998-03-23 | 1998-04-06 | 1998-04-13 | 1998-04-20 | 1998-04-28 | 1998-05-05 | 1998-05-12
Found | 102.5 | 102.5 | 102.5 | 102.5 | 102.5 | 170.8333 | 170.8333 | 170.8333 | 156.3333 | 156.3333 | 78.1667 | 50 | 25
Fix | 38 | 38 | 38 | 38 | 38 | 108 | 108 | 108 | 188 | 188 | 94 | 125 | 125
Backlog | 0 | 64.5 | 129 | 193.5 | 258 | 320.8333 | 383.6667 | 446.5 | 414.8333 | 383.1667 | 367.3333 | 292.3333 | 192.3333 | 67.3333 | -57.6667 | -182.6667 | -307.6667
Total Issues | 102.5 | 205 | 307.5 | 410 | 512.5 | 683.3333 | 854.1667 | 1025 | 1181.3333 | 1337.6667 | 1415.8333 | 1465.8333 | 1490.8333
Current staffing cannot bring bug backlog down in time for planned ship!
OFF by a week.
Functional Total | 1997-09-29: 1025; 1997-12-02: Pre-functional; 1997-12-29: 512.5; 1998-01-26: Functional; 1998-02-23: 512.5
|  |  | per-cycle |  | 102.5 |  | per-cycle |  | 170.8333
System Total | 1997-09-29: 469; 1997-12-02: per-cycle; 1997-12-29: 156.3333
Acceptance Total | 1997-09-29: 100; 1997-12-02: per-cycle; 1997-12-29: 50

## Model Scratch Pad
Scratch Pad
Bug Fix Rate
Bugs
| Rate | Engineers | Adjust | Days | Fixed
Class | per manday |  | (bug fix %) | per cycle | per cycle
Pre-Functional | 3 | 2.5 | 0.5 | 10 | 38 | Little bug fixing during pre-functional testing on spock
Func Complete | 2 | 6 | 0.9 | 10 | 108 | Bug fix time is dedicated.
System Test | 1.5 | 12.5 | 1 | 10 | 188 | System test.
Acceptance | 1 | 12.5 | 1 | 10 | 125 | System/Regression Test
Historical rates
Find rate for Components
Historical Cases
| R | P | D | L | Assume | Split to tests
Total | 6195 | 1585 | 2038 | 2172 | 1594 | <---- Target this at 1600
Feature-A | 162 |  | 40 | 23 | 10 | FUNC | 8
[6 empty] | SYS | 2
Connectivity | 542 |  | 193 | 155 | 300 | FUNC | 225
[6 empty] | SYS | 75
Calculator | 53 |  | 36 | 7 | 8 | FUNC | 6
[6 empty] | SYS | 2
Notes | 265 | 46 | 144 | 65 | 80 | FUNC | 60
[6 empty] | SYS | 20
Feature-B | 118 |  | 230 | 39 | 120 | FUNC | 90
[6 empty] | SYS | 30
Print |  |  |  |  | 100 | FUNC | 75
[6 empty] | SYS | 25
Feature-G | 352 | 174 | 248 | 313 | 260 | FUNC | 195
[6 empty] | SYS | 65
Fax | 228 |  |  | 41 | 40 | FUNC | 30
[6 empty] | SYS | 10
Converter |  |  |  | 26 | 8 | FUNC | 6
[6 empty] | SYS | 2
General UI | 300 |  |  | 26 | 120 | FUNC | 90
[6 empty] | SYS | 30
Feature-O |  |  |  |  | 140 | FUNC | 105
[6 empty] | SYS | 35
Security | 63 |  |  | 6 | 40 | FUNC | 30
[6 empty] | SYS | 10
Services | 310 |  |  | 90 | 40 | FUNC | 30
[6 empty] | SYS | 10
System | 110 |  |  | 45 | 80 | FUNC | 60
[6 empty] | SYS | 20
Feature-Y | 140 |  |  | 57 | 20 | FUNC | 15
[6 empty] | SYS | 5
General System |  |  |  |  | 128 | Profile | 44
[6 empty] | Stress | 80
[6 empty] | File Corrupt. | 4
[5 empty] | 100 | Acceptance
Functional Total | 1025
System Total | 469
Acceptance Total | 100
Total | 1594