## Sheet1
Build Schedule by Milestone
QA Milstones | Module & Functional Test
Project Milestones | Block I & II |  | Block III |  | Block IV
Build Name | QI | QII | QIII | QIV | QV
Build Date (a) | 1997-02-10 | 1997-02-24 | 1997-03-10 | 1997-03-24 | 1997-04-07
Number days of testing | 9 | 10 | 10 | 10 | 5
QA Milstones | Mod.&Func | Alpha |  |  | Beta
| Block IV | Integration | System |  | Field
Build Name | QVI | QVII | QVIII | QIX | QX
Build Date (a) | 1997-04-14 | 1997-04-21 | 1997-04-28 | 1997-05-05 | 1997-05-12
Number days of testing | 5 | 5 | 5 | 5 | 5
QA Milstones | Beta | Branding
| Fix Update | Func. & Regression |  | Field | Fix Update
Build Name | R2QI | R3QI | R3QII | R3QIII | R3QIV
Build Date (a) | <unknown> | <unknown> | <unknown> | <unknown> | <unknown>
Number days of testing | 10 | 5 | 5 | 5 | 5
(a) | Build due to QA at the beginning of this day.

## Sheet2
Tests to Run by Project Milestone
QA Milstones | Module & Functional Test |  |  | Alpha |  | Beta
Project Milestones | Block I &II | Block III | Block IV | Integration | System | Field
Tests
FU-1 |  |  | RUN |  | RUN | RUN
FU-2 |  |  | RUN | RUN | RUN | RUN
FU-3 |  |  | RUN | RUN | RUN | RUN
FU-4 |  |  | RUN |  | RUN | RUN
FU-5 |  |  | RUN |  | RUN | RUN
FU-6 |  | RUN |  |  | RUN
FU-7 |  | RUN |  |  | RUN | RUN
FU-8 | RUN | RUN |  |  | RUN
FU-9 |  |  | RUN |  | RUN
FU-10 | RUN |  |  |  | RUN | RUN
FU-11 | RUN |  |  | RUN | RUN
FU-12 |  | RUN |  | RUN |  | RUN
FU-13 |  | RUN |  | RUN |  | RUN
<deleted>
<deleted>
FU-16 |  | RUN | RUN | RUN | RUN | RUN
FU-17 | RUN |  | RUN |  | RUN | RUN
FU-18 |  | RUN |  |  | RUN | RUN
FU-19 |  | RUN | RUN
FU-20 |  | RUN |  |  | RUN | RUN
FU-21 |  | RUN |  |  | RUN | RUN
FU-22 |  | RUN |  |  | RUN | RUN
FU-23 |  | RUN |  |  | RUN | RUN
FU-24 |  | RUN |  |  | RUN
FU-25 |  |  | RUN
FU-26 | RUN |  | RUN
FU-27 | RUN |  | RUN
FU-28 | RUN |  | RUN
FU-29 | RUN |  | RUN
FU-30 | RUN |  | RUN
FU-31 | RUN |  | RUN
FU-32 | RUN |  | RUN |  | RUN | RUN
FU-33 |  | RUN
FU-34 |  | RUN |  | RUN | RUN | RUN
FU-35 |  | RUN |  |  | RUN | RUN
FU-36 | RUN |  |  |  | RUN
FU-37 |  |  | RUN | RUN | RUN | RUN
FU-38 |  |  | RUN | RUN | RUN | RUN
FU-39 |  |  | RUN |  | RUN
FU-40 | RUN |  |  |  | RUN | RUN
FU-41 |  | RUN |  | RUN | RUN | RUN
FU-42 |  |  | RUN |  | RUN | RUN
FU-43 |  | RUN |  | RUN | RUN | RUN
FU-44 |  | RUN |  | RUN | RUN | RUN
UI-1 |  |  | RUN |  | RUN
Tests to Run by Project Milestone
QA Milstones | Module & Functional Test |  |  | Alpha |  | Beta
Project Milestones | Block I &II | Block III | Block IV | Integration | System | Field
UI-2 |  |  | RUN |  | RUN
UI-3 |  |  | RUN |  | RUN
QA-1 | RUN |  |  |  | RUN
QA-2 | RUN |  |  |  | RUN
QA-3 |  | RUN |  |  | RUN
QA-4 |  |  | RUN |  | RUN | RUN
ISV-1 |  |  |  | RUN | RUN | RUN
ISV-2 |  |  |  | RUN | RUN | RUN
ISV-3 |  |  |  |  | RUN
ISV-4 |  |  |  |  | RUN
ISV-5 |  |  |  | RUN | RUN | RUN
ISV-6 |  |  |  |  | RUN
ISV-7 |  |  |  |  | RUN
ISV-8 |  |  |  |  | RUN | RUN
ISV-9 |  |  |  |  | RUN | RUN
ISR-1 |  |  |  | RUN |  | RUN
ISR-2 |  |  |  | RUN |  | RUN