## Metrics
METRICS |  |  | CWSP Beta-2
= gray means a live, running total
SEL Bugs
| week starting | 2002-11-04 | 2002-11-11 | 2002-11-18
| Total | 13 | 20 | 20
| Entered | 13 | 7 | 0
| Fixed | 0 | 2 | 5
| Open | 13 | 18 | 13
| entered while helping comp. teams | 9 | 16 | 16
Current Snapshot of Bugs
|  |  | OPEN= | 14
|  |  |  | all | open | fixed/closed
|  |  | P1= | 5 | 3 | 2
|  |  | P2= | 9 | 5 | 4
|  |  | P3= | 7 | 6 | 1
|  |  | P4= | 0 | 0 | 0
|  |  | totals= | 21 | 14 | 7
|  |  | Install help (Irene's team)= | 15
|  |  | CQA help (Chandra's team)= | 1
Project Milestones
| item | start | finish | actual | met
| LEVEL-1 : B7b | 2002-11-08 | 2002-11-17 | not | 18.75%
| LEVEL-1 : B7c | 2002-11-18 | 2002-11-24 | not | 0%
| LEVEL-2 : B7d | 2002-11-25 | 2002-12-01 | not | 0%
| RCs | 2002-12-02 | 2002-12-08 | not | 0%
| FINAL Build | 2002-12-09 | 2002-12-15 | not | 0%
| RTM | 2002-12-13 | 2002-12-13 | not | 0%
SEL Tasks
| week | start | met
| week 1 | 2002-11-08 | 0% |  | Abandoned. No working build
| week 2 | 2002-11-18 | 0%
| week 3 | 2002-11-26 | 0%
| week 4 | 2002-12-02 | 0%
| week 5 | 2002-12-09 | 0%
Environments
| server-a on 2k-1 |  | 0%
2-machine
| 1-machine |  | 0%

## SOM
Deliveries by Week |  |  | Named. Each will be one of the above types.
effort complete
2002-11-11 | B7b e1 #1 | B1 | B7b e2 #1 | B2 |  | B3 |  | B4 |  | B5
|  | 2 |  | 2 | [6 empty] | 4 | effort
LEVEL-1 : B7b | no working build | 0% | no (working) build | 0% | [6 empty] | 0% | complete
| 2k-1/server-a | 2 | 2k-1/server-a | 5
2002-11-18 | B7c e1 #1 | C1 | B7c e2 #1 | C2 |  | C3 |  | C4 |  | C5
|  | 1 |  | 1 | [6 empty] | 2 | effort
LEVEL-1 : B7c |  | 0% |  | 0% | [6 empty] | 0% | complete
| 2k-1/server-a | 3 | 2k-1/server-a | 6
2002-11-25 | B7d e1 #1 | D1 | B7d e2 #1 | D2 |  | D3 |  | D4 |  | D5
|  | 1 |  | 1 | [6 empty] | 2 | effort
LEVEL-2 : B7d |  | 0% |  | 0% | [6 empty] | 0% | complete
| 2k-1/server-a | 1 | 2k-1/server-a | 5
2002-12-02 | RC-final e1 #1 | E1 | RC1 e2 #1 | E2 | RC2 e1 #1 | E3 | RC2 e2 #1 | E4 |  | E5
|  | 1 |  | 1 | [6 empty] | 2 | effort
RCs |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0% | complete
| 2k-1/server-a | 1 | 2k-1/server-a | 5
2002-12-09 | RC-final e1 #1 | F1 | RC-final e2 #1 | F2 | FINAL e1 #1 | F3 | FINAL e2 #1 | F4 | RTM Checklist | F%
|  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 5 | effort
FINAL Build |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0% | complete
| 2k-1/server-a | 1 | 2k-1/server-a | 5 | 2k-1/server-a |  | 2k-1/server-a
| color key |  |  |  | box key
| not started |  |  | lab or task name | Lab name | A1 | id
| underway |  |  |  | INFO | # | Effort
| problems |  |  |  | due | % | Completion
| done |  |  | Environment type | type | 5 | Environment type

## Milestones
Milestone Schedule
|  |  |  | scheduled |  | actual finish date
Week Number | Owner |  | item | start date | finish date |  | % met | Notes
criteria for next cycle
| CQA |  | B7b build complete | milestone | 2002-11-08 |  | 0%
1 |  |  | LEVEL-1 : B7b | 2002-11-08 | 2002-11-17 | not | 18.75%
| CQA |  | CBAT Complete B7b | milestone | 2002-11-17 |  | 0%
Lab | SEL | 1 | B7b e1 #1 | 2002-11-12 | 2002-11-13 |  | 0% | Abandon. No build
Lab | SEL | 2 | B7b e2 #1 | 2002-11-09 | 2002-11-11 |  | 0% | Abandon No build
criteria for next cycle
| CQA |  | B7c build complete | milestone | 2002-11-14 |  | 75% | Late
2 |  |  | LEVEL-1 : B7c | 2002-11-18 | 2002-11-24 | not | 0%
| CQA |  | CBAT Complete B7c | milestone | 2002-11-24 |  | 0%
Lab | SEL | 1 | B7c e1 #1 | 2002-11-18 | 2002-11-20 |  | 0%
Lab | SEL | 2 | B7c e2 #1 | 2002-11-15 | 2002-11-18 |  | 0%
criteria for next cycle
| CQA |  | B7d build complete | milestone | 2002-11-21 |  | 0%
| SEL |  | SEL Tests Frozen (no more changes or additions) | milestone | 2002-11-24 |  | 0%
| Docs |  | Draft installation and operation docs available | milestone | 2002-10-06 |  | 0%
5 |  |  | LEVEL-2 : B7d | 2002-11-25 | 2002-12-01 | not | 0%
| CQA |  | CBAT Complete B7d | milestone | 2002-12-01 |  | 0%
Lab | SEL | 1 | B7d e1 #1 | 2002-11-26 | 2002-11-27 |  | 0%
Lab | SEL | 2 | B7d e2 #1 | 2002-11-24 | 2002-11-26 |  | 0%
criteria for next cycle
| CQA |  | B7e (RC1) build complete | milestone | 2002-11-28 |  | 0%
| SEL |  | Final test data ready for all products | milestone | 2002-12-01 |  | 0%
| Dev |  | Perforce locked down | milestone | 2002-12-01 |  | 0%
| SEL |  | No bug backlog (All P1 &P2 defects -> zero) | milestone | 2002-12-01 |  | 0%
6 |  |  | RCs | 2002-12-02 | 2002-12-08 | not | 0%
| CQA |  | CBAT Complete B7e | milestone | 2002-12-08 |  | 0%
Lab | SEL | 1 | RC1 e1 #1 | 2002-12-01 | 2002-12-03 |  | 0%
Lab | SEL | 2 | RC1 e2 #1 | 2002-12-01 | 2002-12-02 |  | 0%
| CQA |  | Interim (RC2) build complete | milestone | 2002-12-04 |  | 0%
Lab | SEL | 3 | RC2 e1 #1 | 2002-12-06 | 2002-12-06 |  | 0%
Lab | SEL | 4 | RC2 e2 #1 | 2002-12-05 | 2002-12-05 |  | 0%
criteria for next cycle
| Dev |  | Code Freeze | milestone | 2002-12-06 |  | 0%
| CQA |  | RC Final/Frozen build complete | milestone | 2002-12-08 |  | 0%
| SEL |  | No bug backlog | milestone | 2002-12-08 |  | 0%
| SQA |  | All component tests run | milestone | 2002-12-08 |  | 0%
| CQA |  | All system tests run | milestone | 2002-12-08 |  | 0%
7 |  |  | FINAL Build | 2002-12-09 | 2002-12-15 | not | 0%
| CQA |  | Final BAT | milestone | 2002-12-10 |  | 0%
Lab | SEL | 1 | RC-final e1 #1 | 2002-12-09 | 2002-12-10 |  | 0%
Lab | SEL | 2 | RC-final e2 #1 | 2002-12-08 | 2002-12-09 |  | 0%
| Dev |  | Final triage (if needed) | milestone | 2002-12-10 |  | 0%
| SEL |  | All bugs closed or defered | milestone | 2002-12-11 |  | 0%
| Dev |  | FINAL build complete (if needed) | milestone | 2002-12-10 |  | 0%
Lab | SEL | 3 | FINAL e1 #1 | 2002-12-11 | 2002-12-11 |  | 0%
Lab | SEL | 4 | FINAL e2 #1 | 2002-12-11 | 2002-12-11 |  | 0%
| Dev |  | Final Build submitted for media burn | milestone | 2002-12-11 |  | 0%
| Rls Eng |  | Create Media | 2002-12-11 | 2002-12-11 |  | 0%
| CQA |  | Media Validation | 2002-12-12 | 2002-12-12 |  | 0%
| SEL |  | RTM Checklist | 2002-12-13 | 2002-12-13 |  | 0%
criteria for next cycle
11 |  |  | RTM | 2002-12-13 | 2002-12-13 | not | 0%
criteria ship
| Rls Eng |  | QA accepts media | milestone | 2002-12-13 |  | 0%
| Perf |  | Final Peformance and Scalability Report delivered | milestone | 2002-12-13 |  | 0%
| CQA |  | QA Reports delivered | milestone | 2002-12-13 |  | 0%
| SEL |  | Known priority 1 and 2 bugs documented in release notes | milestone | 2002-12-13 |  | 0%
Formulas:
finish date = [start date]+9

## Environments
Environment Types |  |  | Numbered by type.
ROES:
server-a on 2k-1 |  |  |  | total | 0%
| 1 | 2-machine | Install successful | 0%
|  | deployment time | Repeat install successful | 0% | total | survey results
|  |  | Passed verification | 0% | 0% | n/a
| 2 | 1-machine | Install successful | 0%
|  | design time | Repeat install successful | 0% | total | survey results
|  |  | Passed verification | 0% | 0% | n/a

## Tasks
Task Pipeline Status
|  |  | Prepare environment | Plan | Install | Configure | Execute | Verify | Clone and release | Document | Desired completion date | % complete
Items listed in week due
week | id | item
week 1 | B | 11 Nov -> 17 Nov | [9 empty] | 0%
| 1 | B7b e1 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-11-13 | 0%
| 2 | B7b e2 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-11-11 | 0%
week 2 | C | 18 Nov -> 24 Nov | [9 empty] | 0%
| 1 | B7c e1 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-11-20 | 0%
| 2 | B7c e2 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-11-18 | 0%
week 3 | D | 25 Nov -> 1 Dec | [9 empty] | 0%
| 1 | B7d e1 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-11-27 | 0%
| 2 | B7d e2 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-11-26 | 0%
week 4 | E | 2 Dec -> 8 Dec | [9 empty] | 0%
| 1 | RC1 e1 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-12-03 | 0%
| 2 | RC1 e2 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-12-02 | 0%
| 3 | RC2 e1 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-12-06 | 0%
| 4 | RC2 e2 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-12-05 | 0%
week 5 | F | 9 Dec -> 15 Dec | [9 empty] | 0%
| 1 | RC-final e1 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-12-10 | 0%
| 2 | RC-final e2 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-12-09 | 0%
| 3 | FINAL e1 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-12-11 | 0%
| 4 | FINAL e2 #1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2002-12-11 | 0%
|  | RTM Checklist | x | x | x | x | 0% | x | x | 0% | 2002-12-13 | 0%
|  |  | Prepare environment | Plan | Install | Configure | Execute | Verify | Clone and release | Document | Desired completion date | % complete
key
build environment instance

## Bugs
Bugs
| # | DB Number | Description | Status | Owner | Priority | Re-opened | DR Issue | Added | Erich's comments
| 1 | 63143 | Bad bug 1 | OPEN | JOHN | 2 | NO | NO | 2002-09-18 | G1 buildout | 2 | 0
| 2 | 63561 | Bad bug 2 | OPEN | JOHN | 1 | NO | YES | 2002-09-27 | Install task | 1 | 0
| 3 | 63965 | Bad bug 3 | OPEN | JOHN | 3 | NO | NO | 2002-10-09 | Install task | 3 | 0
| 4 | 64117 | Bad bug 1 | FIXED | JOE | 1 | YES | NO | 2002-10-11 | A2 | 0 | 1
| 5 | 64273 | Bad bug 2 | FIXED | BOB | 2 | NO | NO | 2002-10-15 | Install task | 0 | 2
| 6 | 64326 | Bad bug 3 | OPEN | BOB | 1 | NO | NO | 2002-10-15 | B2 | 1 | 0
| 7 | 64436 | More Bad bug 1 | OPEN | BOB | 2 | NO | NO | 2002-10-16 | A5 | 2 | 0
| 8 | 65788 | Bad bug 2 | FIXED | JOHN | 1 | NO | NO | 2002-10-29 | Install task | 0 | 1
| 9 | 65800 | More Bad bug 1 | FIXED | JOHN | 2 | NO | NO | 2002-10-29 | Install task | 0 | 2
| 10 | 66454 | Really bad thing happens | OPEN | JOHN | 3 | NO | NO | 2002-11-05 | Install task | 3 | 0
| 11 | 66458 | Bad thing happens | CLOSED | JOHN | 3 | NO | NO | 2002-11-05 | Install task | 0 | 3 | DUP
| 12 | 66456 | Bad bug 3 | FIXED | JOHN | 2 | NO | NO | 2002-11-05 | Install task | 0 | 2
| 13 | 66454 | Bad bug 1 | OPEN | BOB | 3 | NO | NO | 2002-11-06 | Install task | 3 | 0
| 14 | 66764 | Bad bug 2 | OPEN | BOB | 1 | NO | NO | 2002-11-11 | CQA help | 1 | 0
| 15 | 66807 | Bad bug 3 | OPEN | JOE | 3 | NO | NO | 2002-11-11 | Install task | 3 | 0
| 16 | 66811 | More Bad bug 1 | OPEN | JOE | 3 | NO | NO | 2002-11-11 | Install task | 3 | 0
| 17 | 66809 | Bad bug 2 | FIXED | JOE | 2 | NO | NO | 2002-11-11 | Install task | 0 | 2
| 18 | 66812 | More Bad bug 1 | OPEN | JOE | 2 | NO | YES | 2002-11-11 | Install task | 2 | 0
| 19 | 66814 | Really bad thing happens | OPEN | JOE | 3 | NO | NO | 2002-11-11 | Install task | 3 | 0
| 20 | 66816 | Bad thing happens | OPEN | JOE | 2 | NO | NO | 2002-11-11 | Install task | 2 | 0
| 21 | 67481 | Really bad thing happens | OPEN | ERICH | 2 | NO | NO | 2002-11-21 | C1 | 2 | 0
[11 empty] | 0 | 0
| nnn | nnnnn | abc | OPEN | JOE | 1 | NO |  |  | abc
|  |  |  | CLOSED | BOB | 2 | YES
|  |  |  | FIXED | JOHN | 3
|  |  |  | POSTPONED | ERICH | 4
|  |  | OPEN= | 14
|  |  |  | all | open | fixed/closed
|  |  | P1= | 5 | 3 | 2
|  |  | P2= | 9 | 5 | 4
|  |  | P3= | 7 | 6 | 1
|  |  | P4= | 0 | 0 | 0
|  |  | totals= | 21 | 14 | 7
|  |  | Install Tasks= | 15
|  |  | CQA help= | 1