## Sheet1
Cycle 5 | 14 Nov 23:00PST
Integration Status |  | MOE 4.6 | [5 empty] | G-Lab
Windows
| Installed | Configured | Trading | Portal (ie, SSO) | Verified | sel owner | install party schedule | build | notes
moe 4.6 | [7 empty] | #5
Platform 4.6 | done | done | n/a | n/a | done | Bob | done | #5
Portal 4.6 | done | done | n/a | n/a | u. | Bob |  | #5
Portal Services 4.6 | - | - | n/a | n/a | - |  |  | #5
Connector 4.6 | - | - | - | n/a | - |  |  | #5
App-3lbox 2.0 | - | - | - | - | - |  |  | #5
App-1 2.0 | - | - | - | - | - |  |  | #5
App-2 | - | - | - | - | - |  |  | #5
Service-1 2.0 | - | - | - | - | - | Bob |  | #5
Service-3 | x | x | x | n/a | x | No build? | No build?
Gateway | optional |  |  |  |  | No build? | No build?
Data Service | - | - | - | n/a | - |  |  | #5
App-3 | - | - | - | - | - |  |  | #5
Tracking | x | x | x | n/a | x | No build? | No build?
Integration Status |  | MOE 4.6 | [5 empty] | Y-Lab
Solaris
| Installed | Configured | Trading | Portal (ie, SSO) | Verified | sel owner | install party schedule | build | notes
moe 4.6 | [7 empty] | #5
Platform 4.6 | done | done | n/a | n/a | done | Joe | done | #5
Portal 4.6 | done | done | n/a | n/a | done | Joe | done | #5
Portal Services 4.6 | - | - | n/a | n/a | - | Joe |  | #5
Connector 4.6 | - | - | - | n/a | - | Joe |  | #5
App-3lbox 2.0 | - | - | - | - | - | Joe |  | #5
App-1 2.0 | - | - | - | - | - | Joe |  | #5
App-2 (on w2k) | - | - | - | - | - | Joe |  | #5
Service-1 2.0 (on w2k) | done | done | u. | u. | - | Joe |  | #5
Service-3 | - | - | - | n/a | - | Joe |  | #5
Gateway | optional |  |  |  |  | No build? | No build?
Data Service | - | - | - | n/a | - |  |  | #5
App-3 | x | x | x | n/a | x | No build? | No build?
Tracking | x | x | x | n/a | x | No build? | No build?
Integration Status |  | MarketSite 4.6 | [5 empty] | Int 4.6 Lab
Windows
| Installed | Configured | Trading | Portal (ie, SSO) | Verified | sel owner | install party schedule | build | notes
moe 4.6
Platform 4.6 | done | done | done | done | done | John | no party | #4
Portal 4.6 | done | done | done | done | done | John | done | #4 | Patched up
Connector 4.6 | done | done | done | done | done | John | no party | #4
App-3lbox 2.0 | done | done | done | done | done | John | done | #4
App-1 2.0 | done | done | u. | u. | u. | John | no party | #4 | Unblocked?
App-2 | - | - | - | - | - | John | no party | #5
Service-1 2.0 | - | - | - | - | - | John | no party | #5
Service-3 | x | x | x | n/a | x | No build? | No build?
Gateway | x | x | x | n/a | x | John | no party | #5
marketsite solution
App-4 3.5 | done | done | done | done | done | John | done | #4
App-5 4.1 SP2 (w2k) | x | x | n/a | x | x | not scheduled | not scheduled
App-6 | x | x | n/a | x | x | not scheduled | not scheduled
Integration Status |  | MarketSite 4.6 | [5 empty] | Int 4.6 S Lab
Solaris
| Installed | Configured | Trading | Portal (ie, SSO) | Verified | sel owner | install party schedule | build | notes
moe 4.6
Platform 4.6 | loaded as needed |  |  |  |  | not scheduled | not scheduled
Portal 4.6 | loaded as needed |  |  |  |  | not scheduled | not scheduled
Connector 4.6 | loaded as needed |  |  |  |  | not scheduled | not scheduled
App-3lbox 2.0 | x | x | x | x | x | not scheduled | not scheduled
App-1 2.0 | x | x | x | x | x | not scheduled | not scheduled
App-2 | x | x | x | x | x | not scheduled | not scheduled
Service-1 2.0 | x | x | x | x | x | not scheduled | not scheduled
Service-3 | x | x | x | n/a | x | not scheduled | not scheduled
Gateway | n/a | n/a | n/a | n/a | n/a | not scheduled | not scheduled
marketsite solution
App-4 3.5 | x | x | x | x | x | not scheduled | not scheduled
App-5 4.1 SP2 (w2k) | loaded as needed |  |  |  |  | not scheduled | not scheduled
Integration Status |  | MarketSite 4.1 w/ 4.6 Apps | [5 empty] | Elements Lab
W2K
| Installed | Configured | Trading | Portal (ie, SSO) | Verified | sel owner | install party schedule | build | notes
moe 4.6
Mailbox 2.0 | - | - | - | - | -
App-1 2.0 | done | done | done | done | done | Mike | no party | #4 | Old build is actually patched higher than build #5
App-2 | done | done | done | done | done | Mike | no party | #4
Service-1 2.0 | - | - | - | - | - | Mike
Service-3 | x | x | x | n/a | x | No build? | no party | #5
Gateway | n/a | n/a | n/a | n/a | n/a |  |  |  | SLA done
marketsite solution
App-4 3.5 | done | done | done | done | done | Mike | done | #5
App-5 4.1 SP2 (w2k) | done | done | n/a | done | - | Erich | no party | #5
App-6 | - | - | n/a | - | - | Erich |  | #5
| status key | [6 empty] | build key
| - |  | = Not yet |  |  |  |  | - | = no build taken
| u. |  | = work underway |  |  |  |  | new | = new build taken
| DOA |  | = not software available |  |  |  |  | old | = old build taken
| Prob |  | = problems encountered |  |  |  |  | exist | = old install used
| Done |  | = done
| Avl |  | = for Platform/Portal 4.6 availability
| x |  | =install canceled do to cascading problems or limited time.