## fixrates
Project-X
Test cycles | Dates | Incoming | Fixed | Closed
SQI | 9/29/97-10/6/97 | 126 | 28 | 15
| 10/7/97-10/13/97 | 7 | 1 | 0
| 10/14/97-10/20/97 | 8 | 4 | 3
| 10/21/97-10/27/97 | 9 | 5 | 0
| 10/28/97-10/31/97 | 11 | 5 | 1
SQII | 11/3/97-11/10/97 | 18 | 14 | 14
| 11/11/97-11/17/97 | 9 | 6 | 2
| 11/18/97-11/24/97 | 30 | 2 | 9
| 11/25/97-12/1/97 | 20 | 0 | 1
| 12/2/97-12/8/97 | 4 | 2 | 0
| 12/9/97-12/12/97 | 12 | 0 | 3
SQIII | 12/15/97-12/20/97 | 9 | 0 | 16
SQIV | 12/22/97-12/29/97 | 23 | 4 | 5
| 12/30/97-1/5/98 | 5 | 5 | 0
| 1/6/98-1/9/98 | 10 | 4 | 1
SQV | 1/12/98-1/19/98 | 22 | 4 | 9
| 1/20/98-1/23/98 | 9 | 4 | 0
SQVII | 1/26/98-2/2/98 | 19 | 15 | 2
| 2/3/98-2/6/98 | 17 | 8 | 4
SQVIII | 2/9/98-2/16/98 | 13 | 21 | 14
| 2/17/98-2/20/98 | 44 | 11 | 9
SQIX | 2/23/98-3/2/98 | 62 | 27 | 12
| 3/3/98-3/6/98 | 34 | 19 | 16
SQX | 3/9/98-3/16/98 | 77 | 18 | 22
| 3/17/98-3/20/98 | 28 | 22 | 14
SQXI | 3/23/98-3/30/98 | 57 | 31 | 22
| 3/31/98-4/3/98 | 40 | 43 | 13
SQXII | 4/6/98-4/13/98 | 6 | 40 | 13
| 4/14/98-4/17/98 | 28 | 23 | 21
SQXIII | 4/20/98-4/24/98 | 35 | 18 | 36
| 4/27/98-5/1/98 | 39 | 17 | 36
SQXIV | 5/4/98-5/8/98 | 24 | 27 | 26
| 5/11/98-5/15/98 | 48 | 16 | 20
SQXV | 5/18/98-5/22/98 | 30 | 34 | 20
| 5/25/98-5/27/98 | 22 | 9 | 2
SQXVI | 5/28/98-6/4/98 | 39 | 30 | 70
| 6/5/98-6/12/98 | 36 | 20 | 35
SQXVII | 6/15/98-6/19/98 | 22 | 31 | 21
| 6/22/98-6/26/98 | 33 | 23 | 22
SQXVIII | 6/29/98-7/2/98 | 24 | 13 | 21
| 7/3/98-7/10/98 | 50 | 19 | 24
SQXIX | 7/11/98-7/17/98 | 50 | 17 | 11
| 7/18/98-7/24/98 | 38 | 13 | 17
SQXX | 7/25/98-7/31/98 | 22 | 12 | 9
SQXXI | 8/1/98-8/7/98
SQXXII | 8/8/98-8/14/98
SQXXIII | 8/15/98-8/21/98
SQXXIV | 8/22/98-8/28/98

## backlog
DEFECTS BACKLOG DATA
DATES | UNRESOLVED | OPEN(Hi/Cr) | FIXED | RESOLVED
1997-11-11 | 39 | 17 | 14 | 30
1997-11-18 | 92 | 35 | 24 | 43
1997-11-25 | 106 | 35 | 33 | 67
1997-12-02 | 199 | 48 | 40 | 70
1997-12-09 | 204 | 49 | 37 | 82
1997-12-15 | 250 | 47 | 30 | 109
1997-12-22 | 228 | 40 | 36 | 150
1997-12-30 | 235 | 43 | 39 | 157
1998-01-06 | 217 | 41 | 63 | 183
1998-01-12 | 221 | 43 | 59 | 188
1998-01-20 | 235 | 48 | 62 | 193
1998-01-26 | 237 | 58 | 72 | 203
1998-02-03 | 254 | 59 | 84 | 221
1998-02-09 | 247 | 55 | 89 | 240
1998-02-17 | 263 | 63 | 94 | 249
1998-02-23 | 282 | 65 | 83 | 259
1998-03-03 | 302 | 69 | 115 | 304
1998-03-09 | 331 | 72 | 114 | 334
1998-03-17 | 404 | 81 | 130 | 355
1998-03-23 | 395 | 83 | 139 | 400
1998-03-31 | 418 | 78 | 165 | 458
1998-04-06 | 389 | 81 | 210 | 536
1998-04-14 | 364 | 87 | 221 | 578
1998-04-20 | 371 | 92 | 209 | 615
1998-04-27 | 386 | 93 | 209 | 656
1998-05-04 | 384 | 87 | 175 | 711
1998-05-11
1998-05-18
1998-05-25
1998-06-01
1998-06-05
1998-06-12
1998-06-15

## metrics
QA Metrics for Project-X
The following metrics show number of tests that were executed every test cycle
against listed apps.
QA Test Cycles | Tests Run | Tests Failed | Tests N/R | Pass to Plan | Pass to Run | Applications tested
SQI | 280 | 15 | 33 | 84.66% | 94.64% | Notes, GUI.
SQII | 716 | 24 | 55 | 89.75% | 96.65% | Notes, Contacts,
Clock, Converter,
Calculator
SQIII | 425 | 9 | 45 | 88.51% | 97.88% | Calendar, GUI
SQIV | 747 | 26 | 485 | 58% | 96% | Contacts, Fax, MMC
System
SQVI | 669 | 206 | 34 | 72% | 94% | Contacts, Calendar
Imp/Exp, File Transfr,
Install/Remove
SQVII | 657 | 20 | 235 | 71.41% | 96.96% | Calendar, Contacts
Imp/Exp, Internet
SQVIII | 900 | 50 | 231 | 75.15% | 94.44% | Backup/Restore,
Contacts, MMC,
Notes
SQIX | 943 | 18 | 150 | 84.63% | 98.09% | Calendar, Contacts
Imp/Exp, Sp2Sp,
Contacts
SQX | 1097 | 20 | 255 | 79.66% | 98.18% | Calendar Imp/Exp,
Install/Remove, Notes,
Services, Fax, System
SQXI | 1094 | 45 | 182 | 82.21% | 95.89% | Backup/Restore,
Contacts, Calendar, Print
SQXII | 338 | 11 | 150 | 67.01% | 96.75% | Backup/Restore, MMC
Install/Remove,
SQXIII | 1249 | 34 | 457 | 71.22% | 97.28% | Contacts, Spock2
Calendar, Security
SQXIV |  |  |  | #DIV/0! | #DIV/0! | Backup/Restore,
Install/Remove, Calendar
Imp/Exp, Contacts Imp/Exp,
Printing, File_Transfer
SQXV |  |  |  | #DIV/0! | #DIV/0! | Calendar, Contacts,
System, Profile
SQXVI |  |  |  | #DIV/0! | #DIV/0! | Contacts, Contacts Imp/exp,
Calendar, Calendar Imp/Exp,
Backup/Restore
SQXVII |  |  |  | #DIV/0! | #DIV/0! | Spock2Spock, Notes,
Security, Install/Remove,
Remote Synch, Print, Services
SQXVIII |  |  |  | #DIV/0! | #DIV/0! | Desktop Conn., Contacts